## Features + Technologies Release
Features + Technologies Release Backlog |  |  |  | High-level overview of which features are planned to be released by which Sprint
User | Features | Platform | Technology | Estimates | Sprint 1 | Sprint 2 | Sprint 3
Journal User | I can log how I feel at the start, middle, and end of the day (Very Good, Good, Neutral, Bad, Very Bad), so that I can track how I’m doing each day. | Mobile + Web | Frontend: Mobile - Android Kotlin Web - ReactJS Backend: Spring Boot |  | X
| I can log certain lifestyle activities for the day (How many hours of sleep did I get? How much water did I drink? Did I OT today? etc.), so that I can see if there is correlation with my mood. | Mobile + Web | Frontend: Mobile - Android Kotlin Web - ReactJS Backend: Spring Boot |  | X
| I can write and submit multiple text journal entries for each day, so that I can express my feelings and log events of the day. | Mobile + Web | Frontend: Mobile - Android Kotlin Web - ReactJS Backend: Spring Boot |  | X
| I can have my journal entry be analysed to predict what emotions I was feeling on the day. | Mobile + Web + RESTful API to Python ML model deployed on Flask Server (Sentiment Analysis GoEmotions dataset (created by Google)) | Frontend: Mobile - Android Kotlin Web - ReactJS Backend: Spring Boot Machine Learning Model: HuggingFace API |  |  | X
| I can view all my past journal, mood, and analysis entries. | Web | Frontend: ReactJS Backend: Spring Boot |  |  | X
| I can view a dashboard chart of how I feel, lifestyle activity choices, and word cloud of emotions, to see trends | Web | ReactJS, Material UI, Nivo Charts, Formik, Yup, FullCalendar, and Data Grid |  |  |  | X
| I can accept or reject view requests from Counsellor users, so that I can link up with my mental health professional. | Web + Mobile | Frontend: Mobile - Android Kotlin Web - ReactJS Backend: Spring Boot |  |  | X
Therapist / Counsellor | I can send access request to my client / patient, for their approval. | Web | Frontend: Mobile - Android Kotlin Web - ReactJS Backend: Spring Boot |  |  | X
| I can view all entries and mood + emotion trends of all my clients who accepted view request | Web | Frontend: Mobile - Android Kotlin Web - ReactJS Backend: Spring Boot |  |  | X
| I can view dashboard chart of my individual clients’ mood (user submitted, 1-5 scale), lifestyle activity amounts, and word cloud of emotions | Web | ReactJS, Material UI, Nivo Charts, Formik, Yup, FullCalendar, and Data Grid |  |  |  | X

## Project Status Report
Project Status Report |  |  |  |  | Web |  |  |  |  | Mobile
User | Features | Platform | Technology | In-charge | Requirements | Development | Integration Testing | Deployed to Cloud | In-charge | Requirements | Development | Integration Testing | Deployed to Cloud
Journal User | I can log my mood, and my journal text entry at any point in the day, to capture how I feel at that moment | Mobile + Web | Frontend: Mobile - Android Kotlin Web - ReactJS Backend: Spring Boot | Dion (Backend), Hiroyo (Frontend) | C | Backend: C Frontend: C | C | C | Ma Li + Thina | C | C | C | NA
| I can have my journal entry be analysed to predict what emotions I was feeling on the day. | Mobile + Web + RESTful API to Python ML model deployed on Flask Server (Sentiment Analysis GoEmotions dataset (created by Google)) | Frontend: Mobile - Android Kotlin Web - ReactJS Backend: Spring Boot Machine Learning Model: HuggingFace API | Hiroyo (ML Model, Flask) | ML Model: C Flask: C | ML Model: C Flask: C | C | C | Ma Li + Thina | C | C | C | NA
| I can log certain lifestyle activities for the day (How many hours of sleep did I get? How much water did I drink? Did I OT today? etc.), so that I can see if there is correlation with my mood. | Mobile + Web | Frontend: Mobile - Android Kotlin Web - ReactJS Backend: Spring Boot | Dion (Backend), Hiroyo (Frontend) | C | Backend: C Frontend: C | C | C | Ma Li + Thina | C | C | C | NA
| I can view all my past journal, mood, and analysis entries. | Web | Frontend: ReactJS Backend: Spring Boot | Dion (Backend), Hiroyo (Frontend) | C | Backend: C Frontend: C | C | C | Ma Li + Thina | C | C | C | NA
| I can view a dashboard chart of how I feel, lifestyle activity choices, and word cloud of emotions, to see trends | Web | ReactJS, Material UI, Nivo Charts, Formik, Yup, FullCalendar, and Data Grid | Dion (Frontend + Backend) | C | Backend: C Frontend: C | C | C | NA | NA | NA | NA | NA
| I can accept or reject view requests from Counsellor users, so that I can link up safely with my mental health professional. | Web + Mobile | Frontend: Mobile - Android Kotlin Web - ReactJS Backend: Spring Boot | Dion (Backend), Hiroyo (Frontend) | C | Backend: C Frontend: C | C | C | Ma Li + Thina | C | C | C | NA
Therapist / Counsellor | I can send access request to my client / patient, for their approval. | Web | Frontend: Mobile - Android Kotlin Web - ReactJS Backend: Spring Boot | Dion (Backend), Shengyi (Frontend) | C | Backend: C Frontend: C | C | C | Ma Li + Thina | C | C | C | NA
| I can view all entries and mood + emotion trends of all my clients who accepted view request | Web | Frontend: Mobile - Android Kotlin Web - ReactJS Backend: Spring Boot | Dion (Backend), Shengyi (Frontend) | C | Backend: C Frontend: C | C | C | Ma Li + Thina | C | C | C | NA
| I can view dashboard chart of my individual clients’ mood (user submitted, 1-5 scale), lifestyle activity amounts, and word cloud of emotions | Web | ReactJS, Material UI, Nivo Charts, Formik, Yup, FullCalendar, and Data Grid | Dion (Frontend + Backend) | C | Backend: C Frontend: C | C | C | Ma Li + Thina | NA | NA | NA | NA

## Sprint 0
Sprint 0
Deliverables | IC | Completed?
UI Screens (Web) | Dion | TRUE
UI Screens (Android) | Ma Li, Thina | TRUE
Finalised Use Case Diagram | Dion | TRUE
Prioritised Product Backlog (this) | Dion | TRUE
Individual Contribution Report | All | TRUE
Project Status Report | Dion | TRUE

## Sprint 1
Sprint 1
Targeted Deliverables | Theme | Frontend 1 | Frontend 2 | Backend | Component | Overall IC | Overall Completed (including integration)? | IC Backend | Backend Completed? | IC Frontend 1 | Completed? | IC Frontend 2 | Completed?
Database Schema | Database | Diagram | NA | MySQL | Software Architecture | Dion | TRUE | Dion | TRUE | NA | TRUE | NA | TRUE
Logical Data Model | Database | Diagram | NA | NA | Software Architecture | Dion | TRUE | Dion | TRUE | NA | TRUE | NA | TRUE
Log how they feel at 3 points in day | User Journal Day Entry | ReactJS | Android | Spring Boot | Evolutionary Prototype | Dion | TRUE | Dion | TRUE | Dion | TRUE | Ma Li | TRUE
Log lifestyle activities | User Journal Day Entry | ReactJS | Android | Spring Boot | Evolutionary Prototype | Dion | TRUE | Dion | TRUE | Dion | TRUE | Thina | FALSE
Log text entry | User Journal Day Entry | ReactJS | Android | Spring Boot | Evolutionary Prototype | Dion | TRUE | Dion | TRUE | Dion | TRUE | Ma Li | TRUE
Get prediction | ML Microservice | NA | NA | Python Flask | Evolutionary Prototype | Hiroyo + Shengyi | TRUE | Shengyi | TRUE | NA |  | NA
Model training | ML Model | NA | NA | Python | Evolutionary Prototype | Hiroyo | TRUE | Hiroyo | TRUE | NA |  | NA

## Sprint 2
Sprint 2
Targeted Deliverables | Theme | Frontend 1 | Frontend 2 | Backend | Overall IC | IC Backend | Backend Completed? | IC Frontend 1 | Frontend 1 Completed? | IC Frontend 2 | Frontend 2 Completed?
CI/CD pipeline for ML model | DevSecOps (ML Model) | NA | NA | NA | Hiroyo |  | TRUE |  | FALSE |  | FALSE
Login interface and creation interface | User and Counsellor's login and create | Android | ReactJS | Spring Boot | - | Dion | TRUE | MA LI | TRUE | Dion | TRUE
The Home page of the user | User's home page | Android | ReactJS | Spring Boot | - | Dion | TRUE | MA LI | TRUE | Dion | TRUE
The Home page of the counsellor | Counsellor home page | Android | ReactJS | Spring Boot | - | Dion | TRUE | MA LI | TRUE | Shengyi | FALSE
Mood screen and call backend | Mood screen | Android | ReactJS | Spring Boot | - | Dion | TRUE | MA LI | TRUE | Shengyi | FALSE
Habit screen and call backend | Habit screen | Android | ReactJS | Spring Boot | - | Dion | TRUE | MA LI | TRUE | Shengyi | FALSE
Journal Screen(Counsellor) |  | Android | ReactJS | Spring Boot | - | Dion | TRUE | Thina | FALSE | Shengyi | FALSE
Journal Detail Screen (Counsellor) |  | Android | ReactJS | Spring Boot | - | Dion | TRUE | Thina | FALSE | Shengyi | FALSE
Deploy Spring Boot Backend to Cloud | Integration Testing | NA | NA | Spring Boot | Dion | Dion | TRUE | NA | NA | NA | NA

## Sprint 3
Sprint 3
Targeted Deliverables | Theme | Frontend 1 | Frontend 2 | Backend | Overall IC | IC Backend | Backend Completed? | IC Frontend 1 | Frontend 1 Completed? | IC Frontend 2 | Frontend 2 Completed?
CI/CD pipeline for backend and database | DevSecOps (backend, database) |  |  |  | Dion |  | FALSE |  | FALSE |  | FALSE
The Home page of the counsellor | Counsellor home page | Android | ReactJS | Spring Boot | - | Dion | TRUE | MA LI | TRUE | Shengyi | TRUE
Journal Screen (User) | Past Entries Screen (Journal) |  | ReactJS | Spring Boot | - | Dion | TRUE |  | FALSE | Hiroyo | TRUE
Journal Detail Screen (User) | Past Entries Screen (Journal) |  | ReactJS | Spring Boot | - | Dion | TRUE |  | FALSE | Hiroyo | TRUE
Habits Entries Screen (User) | Past Entries Screen (Habits) |  | ReactJS | Spring Boot | - | Dion | TRUE |  | FALSE | Hiroyo | TRUE
View Link Requests Page (User) | User - Counsellor Link |  | ReactJS | Spring Boot | - | Dion | TRUE |  | FALSE | Hiroyo | TRUE
Accept / Deny link request (User) | User - Counsellor Link |  | ReactJS | Spring Boot | - | Dion | TRUE |  | FALSE | Hiroyo | TRUE
View Link Requests Page (Counsellor) | User - Counsellor Link |  | ReactJS | Spring Boot | - | Dion | TRUE |  | FALSE | Shengyi | TRUE
Send link request (Counsellor) | User - Counsellor Link |  | ReactJS | Spring Boot | - | Dion | TRUE |  | FALSE | Shengyi | TRUE
View Linked Users (Counsellor) | Counsellor Views |  | ReactJS | Spring Boot | - | Dion | TRUE |  | FALSE | Shengyi | TRUE
View Linked User Journal Entries (Counsellor) | Counsellor Views |  | ReactJS | Spring Boot | - | Dion | TRUE |  | FALSE | Shengyi | TRUE
View Linked User Habits Entries (Counsellor) | Counsellor Views |  | ReactJS | Spring Boot | - | Dion | TRUE |  | FALSE | Shengyi | TRUE
User Dashboard | Dashboard (User) | NA | ReactJS | Spring Boot | - | Dion | TRUE |  | FALSE | Dion | TRUE
Counsellor Dashboard | Dashboard (Counsellor) | NA | ReactJS | Spring Boot | - | Dion | TRUE |  | FALSE | Dion | TRUE
Connect to the ml with the emtion | Mood screen | Android |  |  |  |  | FALSE | MA LI | TRUE |  | FALSE